## english
Schedule
Attention: (CMMI is a very serious international qualification certification, all personnel must cooperate strictly and seriously) 1. Daily working hours start at 12:00, conference tool is Zoom, backup tool is VooV Meeting. 2. The relevant personnel only need to pay attention to the time they attend the meeting, and they need to prepare to enter the teleconference 10-15 minutes before the meeting they attend. 3. The time not arranged on the schedule is the work of document translation and arrangement, which has nothing to do with the interviewers. 4. ATM needs full participation. Project 1： Project 2： Project 3： Project 4： Project 5：
Date | Time | Meeting content | Participants (Roles) | Participants' names | ZOOM ID

## chinese
评估访谈安排计划
重要（CMMI是很严肃的国际资质认证，所有人员必须严格、 认真配合） 1、每天工作时间为12:00开始，会议工具为ZOOM，备用工具为腾讯会议 2、相关人员只需要关注自己参加会议的时间即可，需要在自己参加的会议前10-15分钟开始准备进入远程会议 3、不需要参加会议的时间，全部是资料翻译和工作整理，和访谈人员没有关系 4、ATM需要全程参与 项目1、北建大科技园云孵化平台 项目2、航天云网业务门户改版 项目3、云端营销平台 项目4、黄埔智造云-工业互联应用平台 项目5、轴承行业工业互联网协同云平台（一期）
日期 | 时间 | 工作 | 参与人员 | 名字 | ZOOM ID
2021-05-24 | 12:00-12:30 | 启动会议 | 全体
| 12:30-13:30 | 管理层访谈 | 高层
| 13:45-16:00 | 项目经理PM访谈 | PM
2021-05-25 | 13:30-15:00 | 技术小组1访谈 | 技术团队
| 15:15-16:45 | 技术小组2访谈 | 技术团队
| 17:00-18:00 | 组织级培训访谈 | OT
2021-05-26 | 12:00-14:00 | 过程&质量保证访谈 | EPG,QA
| 14:15-15:15 | 追加访谈（如必需的话）
2021-05-27 | 12:00-13:15 | 进行初步发现会议
2021-05-27 | 13:00-14:00 | 进行初步发现会议
2021-05-28 | 12:00-13:15 | 进行最终发现会议 | 全体 | ————
| 13:15-14:15 | 文件整合，归档 | 发起人，评估组成员