## Risk Identification and Manage
* Risk Name | * Risk Category | * Other Risk Category Name | * Risk Description | * Risk Impact | * Risk Mitigation | * Risk Status
1) ATM may become ill | Personnel |  | One of the appraisal team members may become ill or unavailable during the appraisal. | Low | 1) Excluding the LA, plan for 4+ ATMs. 2) LA will work as an ATM if required. 3) Setup the schedule so that all appraisal team members are in all affirmation interviews. | Closed
2) Virtual Tool Failure | Other | Virtual technology | DVS (Demix virtual services) tools may become unavailable due to network failures. | High | 1) Ensure that backup network facilities are available. 2) Ensure that additional overtime is planned and agreed upon should technical difficulties cause appraisal work disruptions. 3) Conduct a test of virtual technologies before the opening briefing. 4) Use Voov as a backup technology. 5) Setup WeChat and WhatsApp groups for backup communication when a failure occurs (between ATL, ATMs, RI and Site-coordinator) | Closed
3) Confidentiality breaches as result of Virtual Delivery. | Other | Virtual Delivery | Potential Confidentiality breaches could happen when participant meetings and ATM meetings happen when using Virtual Delivery methods. | High | 1) Separate interview meetings, appraisal team meetings and presentations [van Zyl, Pieter] 2) The ATL (Appraisal Team Leader) will control access to the above meetings to ensure Confidentiality is maintained [van Zyl, Pieter] 3) All meetings will be scheduled with passwords to assist to control access to the meetings, assisting that Confidentiality is maintained [van Zyl, Pieter] | Closed
4) Virtual Delivery Toolset being new | Other | Virtual Delivery | The usage of DVS (Demix virtual services) tools is new or unfamiliar with some participants and ATMs. | Medium | 1) Ensure DVS tools are tested before the on-site period starts, with ATMs, interpreters, participants and site co-ordinators to ensure tools are installed and users know how to use them. [van Zyl, Pieter] 2) Conduct a desktop review of Demix virtual services (DVS) using the CMMI institute EVSD practice area before the start of DVS operations and affect relevant improvements. [van Zyl, Pieter] 3) After each appraisal, use the CMMI Virtual Delivery reporting template to obtain feedback on DVS practices and improve it accordingly. [van Zyl, Pieter] | Closed
5) CMMI Model is new to Appraisal Team | Schedule |  | The CMMI model and MDD are new or unfamiliar to some participants and ATMs, which could affect the appraisal schedule (and potentially quality). | Medium | 1) Ensure enough time scheduled for appraisal activities to allow for possible delays, because the team is learning the new model and CAS system. [van Zyl, Pieter] 2) Update the Demix appraisal templates used by the appraisal team and ATL, to align with the new model and MDD. [van Zyl, Pieter] 3) Facilitate information sharing between appraisal team members and Demix ATL's about the new model and MDD usage. [van Zyl, Pieter] 4) Let ATM's with experience of work with ATM's that are new, where possible. [van Zyl, Pieter] | Closed
6) Confidentiality breach due to unknown participants in Virtual setting | Other | Virtual technology | 1) The virtual environment may cause unwanted visitors to attend interviews and teamwork sessions and as a result breach confidentiality | High | 1) Use a passcode to enable people to join 2) All participants must be visible and their video must be switched on 3) All participants must list their names 4) A waiting room facility will be used 5) Recording features will be disallowed and turned off 6) If required, participants must show their camera 360 degrees so that the appraisal team can see that no other persons are present in the room | Closed
7) Opening Briefing delays due to virtual services | Other | Virtual technology | 1) The virtual services may be new to the organisation and cause delays during the Opening Briefing | Medium | 1) Do a technology-test/participants-briefing the Thursday before the Opening Briefing to make sure all the virtual technologies are working properly | Closed
8) Virtual technology may be blocked by company | Other | Virtual technology | The virtual technology used, such as Zoom, may be blocked by the company's firewalls. | High | 1) Perform a technology test the week before the Opening Briefing to ensure that all firewall entries are open and the virtual technology is functioning between the appraisal team and the participants. 2) Use VooV or Microsoft Teams as backup if needed. | Open
9) Delays due to usage of Virtual technology | Other | Virtual technology | Schedule delays could happen due to the usage of virtual delivery services | High | Note: Some mitigation actions are repeated for other risks above, such as risk #6 1) Plan for additional time at the end of every day in case of virtual services causing delays 2) Plan for using alternative technologies such as Voov as a backup for Zoom (and vice versa). 3) Have an ATL, ATMs, RI and site co-ordinator, WeChat and WhatsApp group to respond immediately to Virtual delivery technology failures. | Open
10) Time zone impacts | Other | Virtual technology | Time zone differences could make the appraisal team less effective. | High | 1) Plan for the forward in the time zone area to start later than normal and the earlier in time zone to start earlier. For example, GMT+8 start at 10:00 is and GMT+2 start at 4:am. | Closed
11) Impact of differences in language | Other | Virtual technology | Language difference could impact the effectiveness of the team | High | 1) Use a bulk document translator to translate all .xlsx, .pptx, and .docx files. These are not perfect translations, but they are good enough. 2) Use additional supporting translation tools such as ChatGPT, Google Translate, and WeChat Translate as needed. | Open
12) Virtual Delivery Practices | Other | Virtual technology | Virtual delivery introduces various risks to the appraisal process | High | 1) Continue to complete and upload the Virtual Delivery Report 2) Continue to complete and upload the Checklist for Virtual Appraisals | Open

## Lookup (hidden)
Personnel | High | Open
Logistics | Medium | Closed
Facilities | Low | Realized
Schedule
Cost
Data
Other
Virtual