## Version History
Version | Date | Description of Change | Approval
<#> |  | <enter description of change>
© 2024 ISACA. All rights reserved.

## CMMI Appraisal Template
Week # | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
| Monday | Monday | Tuesday | Tuesday | Wednesday | Wednesday | Thursday | Thursday | Friday | Friday
| <Enter Date> | <Enter Date> | <Enter Date> | <Enter Date> | <Enter Date> | <Enter Date> | <Enter Date> | <Enter Date> | <Enter Date> | <Enter Date>
8:00 | [10 empty] | Team Activity
8:30 | [10 empty] | Interview/Affirmation
9:00 | [10 empty] | Replanning
9:30 | [10 empty] | Break
10:00
10:30
11:00
11:30
12:00
12:30
13:00
13:30
14:00
14:30
15:00
15:30
16:00
16:30
17:00
17:30
18:00
18:30

## Appraisal Schedule - EXAMPLE
Week 1 | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
| Monday | Monday | Tuesday | Tuesday | Wednesday | Wednesday | Thursday | Thursday | Friday | Friday
| 2013-04-08 | 2013-04-08 | 2013-04-09 | 2013-04-09 | 2013-04-10 | 2013-04-10 | 2013-04-11 | 2013-04-11 | 2013-04-12 | 2013-04-12
8:00 | AT Prep |  | AT Prep |  | AT Prep |  | AT Prep |  | AT Prep |  | Team Activity
8:30 |  |  | AT Review Objective Evidence |  | AT Review Objective Evidence |  | AT Review Objective Evidence |  |  |  | Interview/Affirmation
9:00 | Opening Briefing | [7 empty] | Support: QA/CM/SAM Full Team |  | Replanning
9:30 | [6 empty] | Support: MPM Full Team |  |  |  | Break
10:00 | AT Review Objective Evidence and Team Training
10:30 |  |  |  |  | Security Ops Full Team |  | AT Review Objective Evidence |  | AT Review OE, Consolidate
11:00
11:30
12:00 | Lunch |  | Lunch |  | Lunch |  | Lunch |  | Lunch
12:30
13:00 | AT Review Objective Evidence |  | AT Review Objective Evidence |  | OT/EVW Full Team |  | PM (Erebos, Astreaus, Orama) Full Team |  | AT Review OE, Consolidate
13:30
14:00 |  |  |  |  | AT Consolidate
14:30 |  |  |  |  | Sr. Mgt Full Team |  | AT Review Objective Evidence, Interview Planning
15:00
15:30 |  |  |  |  | AT Consolidate
16:00 | AT Status Check, Replan |  | AT Status Check, Replan |  | AT Status Check, Replan |  | AT Status Check, Replan |  | AT Status Check, Replan
16:30
17:00 | Buffer |  | Buffer |  | Buffer |  | Buffer |  | Buffer
17:30
18:00
18:30
Formulas:
Actual = [Planned]
Planned = [Actual]+1
Planned = [Planned]+1